## WBS
WBS | Task | Phase | Owner | Start | End | Planned | Actual | % | Status
1.0 | Initiation workstream | Initiation | J. Lee | 2026-03-12 | 2026-04-06 | 208333 | 144319 | 73 | In Progress
2.0 | Design workstream | Design | N. Rao | 2026-04-06 | 2026-05-01 | 208333 | 87615 | 43 | In Progress
3.0 | Procurement workstream | Procurement | S. Iyer | 2026-05-01 | 2026-05-26 | 208333 | 152979 | 66 | In Progress
4.0 | Build workstream | Build | N. Rao | 2026-05-26 | 2026-06-20 | 208333 | 51440 | 23 | In Progress
5.0 | Migration workstream | Migration | P. Mehta | 2026-06-20 | 2026-07-15 | 208333 | 27544 | 14 | In Progress
6.0 | Closure workstream | Closure | S. Iyer | 2026-07-15 | 2026-08-09 | 208333 | 89710 | 40 | In Progress

## RAID
Category | Title | Owner | Severity | Prob | Impact | Score | Status
Risk | ISP circuit lead time slip | N. Rao | High | 4 | 4 | 16 | Open
Risk | Change window contention | S. Iyer | Medium | 3 | 3 | 9 | Open
Assumption | Sites accessible in window | PM | Low | 2 | 2 | 4 | Open
Issue | Firmware incompatibility on legacy switches | P. Mehta | High | 5 | 4 | 20 | Open
Dependency | Customer DNS changes | Client | Medium | 3 | 4 | 12 | Open

## Budget
Category | Month | Planned | Actual | Forecast
Hardware | 2026-04 | 50000 | 53243 | 51522
Hardware | 2026-05 | 50000 | 59328 | 50339
Hardware | 2026-05 | 50000 | 48801 | 53721
Hardware | 2026-06 | 50000 | 50463 | 53963
Hardware | 2026-07 | 50000 | 49434 | 52784
Software | 2026-04 | 50000 | 36146 | 49209
Software | 2026-05 | 50000 | 42235 | 48098
Software | 2026-05 | 50000 | 40820 | 48258
Software | 2026-06 | 50000 | 41949 | 52268
Software | 2026-07 | 50000 | 44121 | 50276
Travel | 2026-04 | 50000 | 40238 | 49502
Travel | 2026-05 | 50000 | 58416 | 52360
Travel | 2026-05 | 50000 | 50228 | 48784
Travel | 2026-06 | 50000 | 53228 | 48726
Travel | 2026-07 | 50000 | 44486 | 54921
Services | 2026-04 | 50000 | 51000 | 51677
Services | 2026-05 | 50000 | 52115 | 53821
Services | 2026-05 | 50000 | 54400 | 49218
Services | 2026-06 | 50000 | 35803 | 49866
Services | 2026-07 | 50000 | 41694 | 49082
Labour | 2026-04 | 50000 | 58573 | 54073
Labour | 2026-05 | 50000 | 42867 | 52416
Labour | 2026-05 | 50000 | 44891 | 54359
Labour | 2026-06 | 50000 | 46471 | 49487
Labour | 2026-07 | 50000 | 41166 | 51710

## Changes
CR | Description | Status | Cost Impact | Schedule days
CR-101 | Add 3 additional remote sites to scope | Under Review | 85000 | 21
CR-102 | Upgrade firewalls to next-gen models | Approved | 40000 | 7

## Migration
Type | Site | Status | Acceptance
SD-WAN | Site-01 | Planned | Pending
SD-WAN | Site-02 | Planned | Pending
SD-WAN | Site-03 | Migrated | Accepted
SD-WAN | Site-04 | Migrated | Pending

## Stakeholders
Name | Org | RACI
Programme Sponsor | Royal FRS | A
IT Director | Royal FRS | C
Network Lead | SD Advisory | R