## Slide 1
Weekly Status Report Global WAN / SD-WAN Refresh
Royal FRS | Week ending 2026-06-30 | SD Advisory

## Slide 2
Executive Summary
• Global WAN / SD-WAN Refresh (SD-WAN) for Royal FRS is currently 43% complete and rated Amber. The project is behind schedule (SPI 0.43) and over budget (CPI 0.97). Actual cost to date is 553,607 against a budget at completion of 1,250,000, with an estimate at completion of 1,282,489. Continued focus on the critical path and open RAID items is recommended to protect the execution phase commitments.

## Slide 3
Completed This Period
• Mobilisation activities in progress

## Slide 4
Planned Next Period
• Initiation workstream
• Design workstream
• Procurement workstream
• Build workstream
• Migration workstream
• Closure workstream

## Slide 5
Risks & Issues
• ISP circuit lead time slip (sev High)
• Change window contention (sev Medium)
• Firmware incompatibility on legacy switches

## Slide 6
Budget & Schedule
• Over budget (CPI 0.97, AC 553,607 of BAC 1,250,000, EAC 1,282,489)
• Behind schedule (SPI 0.43, SV -710,416)

## Slide 7
Decisions Required
• Confirm ISP circuit dates
• Finalise rollback runbook